Revised Tentative Tour Programme of the Performance Audit on

“Efficacy of Implementation of 74th Constitutional Amendment Act (CAA)”

- Date of holding the Entry Conference	: 28 September 2020

- Date of commencement of Audit	: 19 October 2020

The date-wise details of the revised tentative tour programme for the Performance Audit to be conducted by the audit team during the period from 19/10/2020 to 05/03/2021 are shown below:

Date-wise details of the Revised Tentative Tour Programme

| Sl. No | Name of Units | Duration of audit |  | Working Days | Sunday(S), Second Saturday (SS) and Holiday (H) |
| --- | --- | --- | --- | --- | --- |
|  |  | From | To |  |  |
| 1 | Principal Secretary, MAHUD1 | 19/10/2020 | 21/10/2020 | 3 | -- |
| 2 | Director, MAHUD | 22/10/2020 | 11/11/2020 | 15 | 24(H), 25(S), 30, 31 & 1(S/H), 8(S) |
| 3 | Secretary, PDA2 | 12/11/2020 | 23/11/2020 | 8 | 14(SS), 15(S), 17(H), 22(S) |
| 4 | Secretary, MUDA3 | 24/11/2020 | 27/11/2020 | 4 | -- |
| 5 | Chief Town Planner, TPD4 | 28/11/2020 | 05/12/2020 | 7 | 29 (S) |
| 6 | Thongkhong Laxmi Municipal Council | 07/12/2020 | 14/12/2020 | 6 | 6(S), 12(H/SS), 13(S) |
| 7 | Kumbi Municipal Council | 15/12/2020 | 21/12/2020 | 6 | 20(S) |
| 8 | Kwakta Municipal Council | 22/12/2020 | 29/12/2020 | 6 | 25(H), 27(S) |
| 9 | Imphal Municipal Corporation | 30/12/2020 | 18/01/2021 | 15 | 1(H), 3(S), 9(SS), 10(S), 17(S) |
| 10 | Ningthoukhong Municipal Council | 19/01/2021 | 25/01/2021 | 6 | 24(S) |
| 11 | Oinam Municipal Council | 27/01/2021 | 02/02/2021 | 6 | 26(H), 31(S) |
| 12 | Wangjing Municipal Council | 03/02/2021 | 09/02/2021 | 6 | 7(S) |
| 13 | Wangoi Municipal Council | 10/02/2021 | 17/02/2021 | 6 | 13(SS), 14(S) |
| 14 | Heirok Nagar Panchayat | 18/02/2021 | 24/02/2021 | 6 | 21(S) |
| Transit to Jiribam 25/02/2020 |  |  |  |  |  |
| 15 | Jiribam Municipal Council | 26/02/2021 | 04/03/2021 | 6 | 28(S) |
| Transit to Imphal 05/03/2021 |  |  |  |  |  |

Note: From Sl. No. 9 to 15, the duration of audit/tour programme may be changed slightly as some of the holidays falling during 2021 could not be reflected due to non-availability of Holiday List of the Government of Manipur for the year 2021.

The audit team would require to frequently visit the MAHUD Directorate, PDA, TPD and IMC as and when needed for collection of information and documents.

Submitted for favour of kind perusal and approval please.

| Sd/- | Sd/- Sr. Audit Officer, AMG-I |
| --- | --- |
| Sr. Audit Officer PA on the “Efficacy of implementation of 74th Constitutional Amendment Act (CAA)” |  |

1Municipal Administration Housing and Urban Development

2Planning and Development Authority

3Manipur Urban Development Agency

4Town Planning Department.