Revised Tentative Tour Programme in respect of Performance Audit on

“Direct Benefit Transfer (Cash transfer only)”

- Date of holding the Entry Conference	: 15 September 2020

- Date of commencement of Audit	: 21 October 2020

The date-wise details of the tentative tour programme for the Performance Audit proposed to be conducted by the audit team during the period from 21/10/2020 to 11/12/2020 are shown below:

Date-wise details of the Tentative Tour Programme

| Sl. No. | Name of Units | Working days | Duration of audit |  | Sunday(S), Second Saturday (SS) and Holiday (H) |
| --- | --- | --- | --- | --- | --- |
|  |  |  | From | To |  |
|  | Directorate of Social Welfare | 7 | 21/10/2020 | 29/10/2020 | 24 (H), 25 (S), 30, 31 & 1 (S) |
|  | RD & PR | 7 | 02/11/2020 | 09/11/2020 | 30, 31 (H), 1 (S), 8 (S) |
|  | Directorate of Social Welfare * | 5 | 10/11/2020 | 17/11/2020 | 14 (SS), 15 (S), 16 (H) |
|  | District Social Welfare Office/DRDA, Chandel | 6 | 18/11/2020 | 24/11/2020 | 22 (S) |
|  | District Social Welfare Office/DRDA, Senapati | 6 | 25/11/2020 | 01/12/2020 | 29 (S) |
|  | District Social Welfare Office/DRDA, Bishnupur | 3 | 02/12/2020 | 04/12/2020 | -- |
|  | District Social Welfare Office/DRDA, Imphal East | 3 | 05/12/2020 | 08/12/2020 | 6 (S) |
|  | State DBT Cell, Secretariat Complex | 3 | 09/12/2020 | 11/12/2020 | - |
|  | Preparation and submission of Draft Report to Principal AG, Manipur | 3rd week of December 2020 |  |  |  |

* Due to Covid infected personnel in the Directorate office, furnishing of information has been delayed by the department.

The audit team would require to frequently visit the following offices as and when needed for collection of information/documents:

- Directorate of Social Welfare

- Directorate of Rural Development and Panchayati Raj

- State DBT Cell, Secretariat Complex

Sd/-

Sr. Audit Officer,

PA on DBT