## Sheet1
Appendix - IX
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
EDUCATION (U) (Technical Education) DEPARTMENT
1 | New Colleges Professional (Govt. Engineering College, Heirok | 2523 | 2019 | 2023 | 90% | 630.75 | 2523 | ... | ... | ...
2 | Nambol Sanoi College Liberal College Thoubal College SE Manipur College (Upgradation of 5 existing college to Model college | 2000 | 2020 | 2023 | 50% | 1000 | 1000 | 1000 | ... | ...
3 | GP Women College Equity Intiative (Construction of 1000 bedded Girl's Hostel) | 500 | 2020 | 2024 | 75% | 125 | 375 | 125 | ... | ...
4 | Construction of model library building at Pettigrew College Ukhrul | 227.46 | 2017 | 2023 | 45% | ... | 94.55 | 132.91 | ... | ...
| Total: | 5250.46 |  |  |  | 1755.75 | 3992.55 | 1257.91
Animal Husbandry and Veterinary including Dairy Farming
1. | Infrastructure Development of 9 District Vety. Hospitals/Vety. Hospital and Establishment of Goat Farm at Heingang, Imphal East under RIDF | ₹1,648.50 a) ₹ 494.55 Vide No. NB. (MNR)/RIDF-XXVI-AH&Vety/2021-22 dated 16/7/2021 as 1st Instalment b) ₹ 369.24 vide No. NB(MNR)/01/RODF-XXVI-MI/2021-22 dated 4/4/2022 as 2nd Instalment | 2021-22 | 2023-24 | 90% | 863.79 | 863.79 | ... | ... | Out of 11 nos., 10 nos. of instalment of 9 District Veterinary Hospitals and 1 Vety. Hospital had been comleted & handover to the Department and Establistment of Goat Farm at Heingang, Imphal East is on-going construction
| Total: | 863.79 |  |  |  | 863.79 | 863.79
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
| 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PUBLIC WORKS DEPARTMENT (PWD)
1 | Infrastructure Development of Noney | ₹1,749.00 26/506/2017-w dt. 19/03/2018 | 2018 | 2024 | 50% | 415 | 415 | 1334 | ... | Work delayed due to non availability of land. Work in progress.
2 | Construction of TD Block at Noney | ₹299.99 126/596/2017-w dt. 15/03/2018 | 2018 | 2023 | 85% | ... | 109.1 | 190.89 | ... | Work delayed due to non availability of land. Work in progress.
3 | Construction of TD Block at Haochong. | ₹299.99 26/588/2017- w dt. 09/03/2018 | 2018 | 2023 | 90% | 79 | 140 | 159.99 | ... | Work in progress.
4 | Impvt. of road from Kwatha Lamkhai to Kwatha Khunou road. | ₹173.18 No.43/368/2019- W dt. 16/03/2020 | 2021 | 2022 | 70% | 50.54 | 50.54 | 122.64 | ... | Work cannot progressed due to prevailing situation of the State.
5 | Construction of Prestigious Nongsaba Gate at Moreh Tengnoupal District. | ₹88.89 No. 26/225/2018- W dated 08/03/2019 | 2022 | 2023 | 70% | 44.14 | 44.14 | 44.75 | ... | Work cannot progrssed due to prevailing situation of the State.
6 | Construction of TD Block at Moreh. | ₹193.53 No. 26/674/2017- w dt 09/03/2018 | 2018 | ... | 60% | 36.46 | 36.46 | 157.07 | ... | Work cannot progrssed due to prevailing situation of the State.
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PUBLIC WORKS DEPARTMENT (PWD)- Contd.
7 | Infrastructure Development for Destination and Circuit (SH; Construction of Administrative Building, Status, landscaping etc. at Marjing Polo Statue including Garden lighting & Facade lighting) | ₹46.25 No. 27/8/2012- TSM (Pt. VIIA) | 2019 | 30/04/2023 as per time extension | 43% | 45 | 91.25 | 296.45 | 341.45 | Time extension under process
8 | Construction of road from Tamah village to IT road 5.00 km | ₹130.00 52/19/2020-w dt. 29/10/2020 | 2021 | 2023 | 90% | 49.25 | 84.25 | 45.75 | ... | Work in progress.
9 | Improvement of Road from Tamei to Katang-21 Km (SH:- Phase-I,0-8.00km). | ₹500.00 52/19/2020-w dt. 29/10/2020 | 2022 | 2024 | 45% | 25.18 | 25.18 | 474.82 | ... | Work in progress.
10 | Improvement of in and around Tamenglong HQ road- 6.00km | ₹200.04 AAEXRF-101/8/2023- WD-WD Dt.23/02/2023. | 2022 | 2023 | 70% | 140.03 | 140.03 | 60.01 | ... | Work in progress.
11 | Strengthening and Widening from km 320.320 to km 330.00 on NH-102, Imphal Moreh Section during the year 2020-21 in the State of Manipur | ₹6,455.29 (NH-12014/04/2020/MN/ ZONE-V) | 2021 | 2023 | 95% | 4229.23 | 4229.23 | 2226.06 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(`` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PUBLIC WORKS DEPARTMENT (PWD)- Contd.
12 | Beautification of roads of National Highways along Greater Imphal Area by providing bituminous layer of the unpaved portion (SH: Providing and laying of bituminous layer along roads of NH:-02 and NH-202 under National Highways Division-III, PWD Manipur) | ₹26,400.00 No. AAEXRF-101/83/2022-WD-WD Dt. 23/06/2022 | 2022 | 2023 | 100% | 2380 | 2380 | 24020 | ...
13 | Construction of Guest House at Poi Village | ₹77.16 No. EE/UD/WO/Bldg/2019-2020/9 dt. 13/11/2020 | 2020 | 2023 | 64% | 25 | 25 | 52.16 | ...
14 | Construction of Rest/Guest House at SALA area Nungbi Khullen Village | 76.48 No. EE/UD/WO/Bldg/2020-2021/8 dt. 13/11/2020 | 2020 | 2023 | 83% | 32.72 | 50.72 | 25.76 | ...
15 | Construction of Guest House at Somdal. | ₹76.72 No. EE/UD/WO/Bldg/2020-2021/7 dt. 13/11/2020 | 2020 | 2022 | 70% | 31 | 31 | 45.72 | ...
16 | Improvement of road from Naimu/Tolloi junction to Teinem/Tuinem 16.00 km | ₹1,139.62 No. 18/1/CE/PW/Bids/UK-02/CRIF/2020-21/8 Dt. 13/07/2022 | 2022 | 2024 | 25% | 50 | 50 | 1089.62 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PUBLIC WORKS DEPARTMENT (PWD)- Contd.
17 | Improvement of road from Ngaimu/Tolloi Junction to Somdal 18 km | ₹1,289.42 No. 18/1/CE/PW/Bids/UK-01/CRIF/2020-21/9 Dt. 13/07/2022 | 2022 | 2024 | 10% | ... | ... | 1289.42 | ...
18 | Improvement of Imphal Ukhrul Road (Old) from New Heaven to Tolloi Junction (Phase-I) | ₹1,498.52 No. EE/UD/WO/CRIF/R&B/2020-2021/1 Dt. 07/01/2022 | 2022 | 2024 | 22% | 36 | 36 | 1462.52 | ...
19 | Improvement of road from Jalenbung to Sanakeithel (Sinakeithel) i/c link Roads. | ₹1,679.44 No. EE/UD/WO/RIDF/R&B/2020-2021/1 Dt. 6/05/2022 | 2022 | 2024 | 67% | 210.01 | 210.01 | 1469.43 | ...
20 | Improvement of internal roads at inter-state bus terminus (ISBT) Khuman Lampak | ₹467.37 No. AAEXRF-101/109/2022-WD-WD Dt. 12/08/2022 | 2022 | ... | 35% | 140 | 140 | 327.37 | ... | Work on halt vide letter No. MISC1-102/15/2022-T(MV)-TPT of Transport Dept. GoM dt. 03/11/2022
21 | Imprvt. of Imphal Saikul road (2.40km to 20.00km) (SH:- Strengthening the existing pavement from 13.350 km to 16.350 km i/c constn. Of 6m span RCC slab culvert at Yumnam Khunou)- Portion -IV | ₹279.15 IE/CT(10)/W/2015- 16/18 Dt. 14/04/2016 | 2016 | 2018 | 89% | 40 | 225 | 54.15 | ...
22 | Impvt. of road from Nongda (Napet Andro Road) Nongdam to Mafou Dam from 0.00 to 14.00 km. | IE/CT (10)/W/20-21/138 Dt. 05/01/2021 ₹ 952.25 | 2021 | 2023 | 90% | ... | 500 | 452.25 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PUBLIC WORKS DEPARTMENT (PWD)- Contd.
23 | Widening of road from Pukhao Lamkhai to Pukhao Terapur at length 0 -3 km. | IE/CT (10)/W/20-21/144 Dt. 11/03/2021 ₹93.78 | 2021 | 2022 | 70% | 25 | 25 | 68.78 | ...
24 | Widening of road from Pukhao Lamkhai to Pukhao Terapur at length 3 - 7 km. | IE/CT (10)/W/20-21/144 Dt. 11/03/2021 ₹117.21 | 2021 | 2022 | 70% | 30 | 30 | 87.21 | ...
25 | Construction of CD Block at Kshetrigao | IE/CT (10)/W/17-18/145 Dt. 11/04/2018 ₹236.23 | 2018 | 2020 | 87% | ... | 89.73 | 146.5 | ...
26 | Constn. of SDO Keirao Bitra (SH:- Constn. of SDO & SDC office and land development). | IE/CT (10)/W/19-20/23 Dt. 16/03/2020 ₹184.52 | 2020 | 2022 | 90% | 27.5 | 127.5 | 57.02 | ...
27 | Impvt. of TK road from Changangei Kabui khul | 43/333/19-w dt. 17/03/20 ₹100.00 | 2020 | 2021 | 50% | 13 | 13 | 87 | ...
28 | Impvt. of Urban Bye pass road from CAU to Punshilok 0.0km to 6.0km and 8.00km to 10.30km. | 43/75/19-w dt. 31/03/20 ₹500.00 | 2021 | 2022 | 87% | 318.4 | 318.4 | 181.6 | ...
29 | Impvt. of Moiranghanuba Sadokpam to Heinoupok road and its neighbouring lanes. | 43/310/19-w dt. 17/03/20 ₹150.00 | 2020 | 2022 | 75% | 90 | 90 | 60 | ...
30 | Impvt. of road from Nambol (on NH-02) to Kamong. | AAEXRF-102/19/20-WD-WD 16.7.21 ₹1,242.95 | 2021 | 2023 | 58% | 517.31 | 517.31 | 725.64 | ...
31 | Impvt. of Church Road via Patsoi. | 42/9/21-w dt 7/1/22 ₹100.00 | 2022 | 2023 | 70% | 30 | 30 | 70 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PUBLIC WORKS DEPARTMENT (PWD)- Contd.
32 | Impvt. of Khurkhul to Sairok | 43/300/17-w dt. 26/02/18 ₹225.00 | 2019 | 2020 | 50% | 65 | 65 | 160 | ...
33 | Impvt. of road from Tiddim road to Khabam Bamdiar Taba road 3kms. | 43/329/19-w dt. 28/03/20 ₹100.00 | 2020 | 2022 | 80% | 60 | 60 | 40 | ...
34 | Impvt. of Keibul Lamjao Lairibam Leirak, Haoreng Tongbram Leiral, Mathak Amyum Leirak Heiga Leiral and Bamon Leirak under Moirang Sub-Division. | ₹100.00 No. 43/155/2018-w dt. 27/03/2020 | 2020 | 2021 | 90% | 45 | 45 | 55 | ... | Work in progress
35 | Construction of Bridge between Ishok Mamang and Ishok Maning over Ishok River | ₹150.00 No. AAEXRF- 1018/8/2023-WD-WD Dt. 23/02/2023 | 2023 | 2024 | 23% | 33 | 33 | 117 | ... | Work in progress
36 | Construction of CD Block at Nambol | ₹300.00 No. 26/677/2017-w dt. 20/03/2017 | 2018 | 2021 | 25% | ... | 32.5 | 267.5 |  | Work halted due to Forest non-clearance
37 | Renovation & Beautification of Single and double room of 4 Nos. Hostels | ₹100.00 No. 26/455/2019-w dt. 24/12/2019 | 2022 | 2023 | 35% | ... | ... | 100 |  | Work in progress
38 | Renovation & Beautification of DLO office 1 & 2 | ₹100.00 No. 26/453/2019-w dt. 24/12/2019 | 2022 | 2023 | 90% | 87.65 | 87.65 | 12.35 |  | Work in progress
39 | Renovation & Beautification of DLO office 3 & 4 | ₹100.00 No. 26/454/2019-w dt. 24/12/2019 | 2022 | 2023 | 90% | 87.65 | 87.65 | 12.35 |  | Work in progress
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PUBLIC WORKS DEPARTMENT (PWD)- Contd.
40 | Reconstruction (widening) of RCC Bridge over Imphal river at Heingang Kangjeibung. | ₹909.87 No. AAEXRF- 102/6/2020-WD-WD Dt. 16/07/2021 | 2022 | 2024 | 83% | ... | 219.83 | 690.04
41 | Construction of 150 ft Bailey bridge over Chakpi river at Mantri Pantha, Chandel | ₹568.00 No. 44/9/2018- w dt. 9/11/2018 | 2021 | 2023 | 79% | 228.4 | 228.4 | 339.6
42 | Constn. of Bridge over Wangjing River at Heirok Chingdongpok. | ₹910.00 No. 44/17/2015-w dt. 31/03/2016 | 2017 | 2023 | 95% | ... | 645.62 | 264.38
43 | Construction of Bailey Bridge over Thoubal River 140 ft span at Khekman, Thoubal District. | ₹299.86 No. AAEXRF- 102/9/2020-WD-WD Dt. 16/07/2021 | 2022 | 2023 | 86% | ... | ... | 299.86
44 | Constn. of Bailey Bridge over Khuga river 170 ft span aat Tuikam, Churachandpur Dist. | ₹451.32 No. AAEXRF- 102-WD-WD Dt. 16/07/2021 | 2022 | 2023 | 78% | ... | ... | 451.32
45 | Construction of RCC Bridge over Leimakhong River at Kamong Meisnam Leikai | ₹300.00 No. 43/391/2019-w dt. 16/03/2020 | 2020 | 2023 | 76% | 45 | 115 | 185
46 | Construction of Bailey Brigde over Manipur river - 180 ft span at chainage 9.30 km on Sekmaijin to Sugunu road (Laphupat Tera Section) | ₹329.94 No. AAEXRF- 102/9/2020-WD-WD Dt. 16/07/2021 | 2022 | 2024 | 98% | ... | 120 | 209.94
47 | Construction of Leisang Hiden Bridge at Pal Ahanbi. | ₹761.72 No. 42/60/2013-w dt. 15/03/2016 | 2016 | 2023 | 70% | ... | 441 | 320.72
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PUBLIC WORKS DEPARTMENT (PWD)- Contd.
48 | Constuction of Prestigious Nongshaba Gate at Jiribam District | ₹107.50 No.AAEXRF-501/7/2023-WD-WD dt. 14/03/2023 | 2021 | 2023 | 90% | 36.00 | 36 | 71.5 | ... | Near Completion
49 | Construction of road from Oinam to Thei Pt. I (0-3 km) | 43/414/2019-W dt. 23.03.2020 ₹216.79 | 2021 | 2022 | 30% | 56.8 | 56.8 | 159.99 | ... | Work in progress
50 | Construction of road from Oinam to Thei Pt. II (3-6 km) | 43/415/2019-W dt. 23.03.2020 ₹211.12 | 2021 | 2022 | 30% | 55.3 | 55.3 | 155.82 |  | Work in progress
51 | Construction of road from Tingsong Khunou to Maichon Border Bridge Pt.I (0-3 km) | 43/416/2019-W dt. 23.03.2020 ₹210.26 | 2021 | 2022 | 40% | 73.4 | 73.4 | 136.86 |  | Work in progress
52 | Construction of road from Tingsong Khunou to Maichon Border Bridge Pt.II (3-6 km) | 43/418/2019-W dt. 23.03.2020 ₹211.26 | 2021 | 2022 | 40% | 73.8 | 73.8 | 137.46 |  | Work in progress
53 | Construction of TD block Phaibung Khullen | 26/608/2017-W dt. 23.03.2018 ₹299.99 | 2018 | 2019 | 81% | 42 | 83 | 216.99 |  | Work in progress
54 | Construction of TD block Willong | 26/706/2017-W dt. 23.03.2018 ₹299.99 | 2018 | 2019 | 80% | 50 | 98.3 | 201.69 |  | Work in progress
55 | Construction of IVR from Ihilo to Khipo at Makhan 4 km | ₹100.00 approved vide A/A No.43/224/2019-W dt. 7.03.2020 | 2020 | 2021 | 30% | ... | 30 | 70 |  | Work in progress
56 | Construction of Prestigous Nongsaba Gate at Mao, Senapati | ₹108.00 approved vide A/A No.26/226/2018-W dt. 08.03.2019 | 2021 | 2022 | 21% | ... | ... | 108 |  | Work in progress
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PUBLIC WORKS DEPARTMENT (PWD)- Contd.
57 | Impvt. of road from NH-02 to Mao Potato farm, Senapati Dist. | ₹693.58 approved vide A/A No.AAEXRF-102/18/2020-WD-WD dt. 16.07.2021 | 2022 | 2024 | 90% | 167.57 | 167.57 | 526.01 |  | Work in progress
58 | Construction of Suspension Bridge connecting two Hillocks at Kakching Garden, Uyokching. | 43/51/2018-w dt. 23/2019 ₹298.37 | 2019 | 2021 | 17% | ... | 50 | 248.37 | ... | Work in progress
59 | Infrastructure Development of Kakching | 26/325/2017-w dt. 17/3/2018 ₹1,292.87 | 2018 | 2024 | 90% | ... | 900 | 392.87 | ... | Work in progress
60 | Infrastructure Development of Basic Ground Kakching | 26/169/2018-w dt. 08/3/2019 ₹153.48 | 2021 | 2024 | 55% | 37.57 | 37.57 | 115.91 | ... | Work in progress
61 | Infrastructure Development of Kamjong (SH: Construction of Divisional Office Block-A) | ₹1,708.73 No. 26/483/2017 -W dt. 23/03/2018 | 2018 | 2023 | 73% | 100 | 800 | 908.73 | ...
62 | Infrastructure Development of Kamjong (SH: Construction of Divisional Office Block-B)
63 | Infrastructure Development of Kamjong (SH: Construction D.C. Bungalow, Security Barrack for Divisional Office and D.C. Bungalow and Security Tower 4 Nos.
64 | Infrastructure Development of Kamjong (SH: Construction of approach road compound fencing culverts and R/wall for Divisional office and D.C. Bungalow)
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PUBLIC WORKS DEPARTMENT (PWD)- Contd.
65 | Construction of TD Block at Sahampung | ₹299.99 No. 26/677/2017- w (Pt.) dt. 24/03/2018 | 2018 | 2023 | 38% | ... | 32.5 | 267.49 | ...
6 | Construction of Road from Kangpat Khunou to Kangkum | ₹150.00 No. 43/81/2018- w (Pt.) dt. 08/03/2019 | 2019 | 2023 | 98% | 12 | 133 | 17 | ...
66 | Improvement of road from Mawai Jn. (BRTF) to Tarong Nambashi (NH-102) road new Jn. | ₹800.00 No. 43/384/2019- w dt. 31/03/2020 | 2020 | 2023 | 21% | 60 | 100 | 700 | ...
67 | Construction of road from Wanglee to Namlee-5 | ₹180.00 No. 43/214/2019- w dt. 16/03/2020 | 2021 | 2023 | 80% | 40 | 80 | 100 | ...
68 | Improvement of Mayang Imphal Anilongbi Yumnam Leikai connecting Sanoujam Leirak (1.1)km Tongbram Leirak (660m), Ningthoujam Leirak (1.5m) Khoirom Lierak (400m) Khoirom Leirak (105m) | ₹120.00 No. 44/134/2019 -w dt. 07/03/2020 | 2020 | 2023-12-01 | 85% | 12 | 80 | 40 | ... | Work in progress
69 | Improvement of road from Samurou Bazar to Mutum Phibou via Imphal Barrage and Iram Siphai. | 52/28/2017 -w(CRF) dt 11/10/2017 ₹624.37 | 2019 | 2023-10-01 | 80% | 80 | 146.13 | 478.24 | ... | Work in progress
70 | Construction of TD Block at Waichong | 26/709/2017 -w dt. 23/03/2018 ₹299.00 | 2018 | 2023 | 90% | 162 | 270 | 29 | ...
71 | Improvement of road from Purum Likli to Wakan -7 km | 43/19/2019-w dt. 17/03/2020 ₹150.00 | 2021 | 2023 | 84% | 43.7 | 98.2 | 51.8 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PUBLIC WORKS DEPARTMENT (PWD)- Contd.
72 | Construction of Bailey Bridge at N. Khobung (Near Motbung) over Imphal River | 43/252/2019 -w dt. 18/03/2020 ₹200.87 | 2021 | 2023 | 95% | 150 | 150 | 50.87 | ...
73 | Improvement of road of block topping of Indira Gandhi National Tribal University (IGNTU) Gate No.2 internal road Makhan Village | 43/51/2019-w dt. 23/03/2020 ₹129.68 | 2021 | 2023 | 75% | 20 | 20 | 109.68 | ...
74 | Improvement of Kangpokpi Internal Road | 52/19/2020-w(A) dt. 16/11/2020 ₹ 880.40 | 2022 | 2024 | 65% | 80 | 105 | 775.4
75 | Improvement of road from Haraithek road to Kharam Vaiphei via L. Phaijang | 43/244/2019-w(Pt) dt. 18/01/2021 ₹125.00 | 2021 | 2023 | 75% | 32.76 | 49.76 | 75.24
76 | Development of two wheeler parking at the basement of Ima Keithel -2 (LUXMI MARKET/IMOINU KEITHEL) | Vide No. 3/16/2020-ISCL. Dt. 09/09/2021 ₹207.00 | 2022-11-29 | 2023-08-28 | 92% | 99.88 | 99.88 | 107.12 |  | Work in progress
77 | Repairing of Nupilal Memorial Complex | 101.80 & 5/14/2011 - AC dt. 04/04/2022 for ₹137.55 | 2022-08-10 | 2022-11-09 | 90% | ... | 54.7 | 82.85 | ... | Work in progress
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PUBLIC WORKS DEPARTMENT (PWD)- Contd.
78 | Construction of Capital Complex (Assembly Component, High Court and Civil Secretariat Component) at Mantripukhri, Imphal (SH: Construction of Approach Bridge over Irong Stream, Approach Road & Pedestrian Bridge at High Court). | W/O Amount ₹80,059.00 Vide No. 26/82/2018 -w dt. 26/12/2018 | 2021-03-23 | 2022-03-21 | 79% | ... | 104.49 | 79954.51 | ... | Work in progress
79 | Construction of Manipur Judicial Academy at Pangei (Phase-I) | ₹709.60 No. Judl. 2/15/2021 SEC-LAW dt. 06/04/2021 | 2022-06-10 | 2022-12-09 | 45% | 322.98 | 322.98 | 386.62 | ... | Work in progress
80 | Renovation of domes of the Assembly Secretariat, Chingmeirong, Imphal East, Manipur. | W/O ₹24,498.567 vide No. EE/BD-I/ tender-Accept/ 2022-23/11 dt. 23/12/2022 & /A for 297.97 & E/S for 282.11 No. MISCWD- 1601/17/2022-WD-WD-Part(I) dt. 19/12/2022 | 2022-11-23 |  | 51% | 30 | 30 | 267.97 | ... | Work in progress
81 | Re-Construction of Imphal East Division office of PWD at Khuyathong PWD Complex | ₹100.00 vide No. 26/117/2019 -w dt 24/12/2019 | 2021-01-11 | 2022-01-10 | 35% | 30 | 30 | 70 | ... | Work in progress
82 | Beautification with ACP cladding of PWD Complex Block A & D Building Khuyathong, Imphal | ₹295.00 vide 26/117/2019-w dt. 24/12/2019 | 2020-03-03 | 2020-09-02 | 25% | ... | 20 | 275 | ... | Work in progress
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PUBLIC WORKS DEPARTMENT (PWD)- Contd.
83 | Addition and alteration of Manipur Bhavan, SP Marg, New Delhi | ₹139.27 No 26/90/2018 -w dt. 20/03/2019 | 2019 | 2020 | 17% | ... | ... | 139.27
84 | Addition and alteration Bir Tikendrajit House, Chanakyapuri New Delhi | ₹294.73 No. 26/91/2018 -w dt. 20/03/2019 | 2019 | 2020 | 8% | ... | ... | 294.73
85 | Construction of SDC office Complex at Salam Keikhu | ₹223.22 No. 26/19/2019 -w (I) dt. 28/08/2019 | 2020 | 2021 | 95% | 48.9 | 125.86 | 97.36
86 | Construction of Chowkidar Qtr., canteen, Vehicle shed RCC Slab Culvert, Gates, Land Development & Black Topping for Employment Exchange at Lamphelpat. | ₹104.99 No. 26/207/2018 -w dt. 08/03/2019 | 2020 | 2022 | 90% | 30 | 30 | 74.99
87 | Construction of Manipur Lokayukta office Building at DC Imphal West Complex, Lamphelpat | ₹1,618.00 No. 26/28/2019- w dt. 30/12/2019 | 2021 | 2022 | 10% | ... | ... | 1618
88 | Constn. of Govt. Qtr. Type-V/F No. 4 at Sanjenthong Offier's Colony occupied by Shri O. Lukhoi (KLA) | ₹167.16 No. 26/20/2019-w (I) dt. 24/08/2019 | 2020 | 2021 | 30% | ... | 50 | 117.16
89 | Constn. of Type-IV Qtrr. (G+I) for accomodation at Lamphelpat (Portion -I) | ₹141.62 No. 26/131/2018-w dt. 08/03/2019 | 2019 | 2019 | 70% | ... | 48 | 93.62
90 | Constn. of Type-IV Qtr. (G+I) for accomodation at Lamphelpat (Portion-II) | ₹141.62 No. 26/133/2018-w dt. 08/03/2019 | 2019 | 2019 | 70% | ... | ... | 141.62
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works & Sanction Order No. | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PUBLIC WORKS DEPARTMENT (PWD)- Contd.
91 | M/O G+2 Court Bldg. and repairing of Compound wall at Cheirap Court Complex, Uripok | ₹145.32 No. 26/568/2017- WD-WD DT. 01/03/2018 | 2018 | 2019 | 95% | ... | 80 | 65.32
92 | Construction of office and Workshop Building for Mechanical Division No. I & II, PWD, Manipur at Kongba Lairenpat | ₹771.69 No. 26/61/2017-W dt. 23/09/2017 | 2020 | 2023 | 61% | ... | 62.64 | 646.15 |  | Work in progress
93 | A) (SH: Constn. of office buiding for Mechanical Division I & II) (South Block)
94 | B) (SH: Constn. of office Building for Mechanical Division I&II (North Block) |  | 2020 | 2023 | 30% | 52.79 | 62.9 | ... |  | Work in progress
| Total : | 1,47,927.68 |  |  |  | 11,760.92 | 17282.28 | 130986.85 | 341.45
TOURISM DEPARTMENT
1 | Infrastructure Development for Destination and Circuit (SH: Constn. of Administrative Building, Statue, Landscapping etc. at Marjing | ₹1,031.15 No. 27/08/2012- TSM (PT.VII) dt. 01/09/2015 (3627.49) | 2016 | 2023 | 95% |  | 3396.09 | 231.4 | 3627.49 vide No.TPT-106/1/2021- TSM-TSM DT. 31/03/2022
| Total : | 3627.49 |  |  |  |  | 3396.09 | 231.4
DEPARTMENT OF INFORMATION TECHNOLOGY (IT)
1 | Constn. of Cafeteria and Renovation of existing building in IT Park Campus at Mantripukhri (SH: Constn. of Cafeteria) | ₹239.56 No. 20/1/2010-DIT (VII-IV) dt. 16/05/2016 | 2017 | 2023 | 95% | 124.79 | 184.21 | 55.35
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
DEPARTMENT OF INFORMATION TECHNOLOGY (IT)
2 | Upgradation of road from Penaching to Heigrutampak via Komlathabi, Purum Chumbang, Laichokching & Thamnapokpi connecting to NH-102 (Indo Myanmar road) | ₹300.00 54/25/2013-W(CRF) dt. 10/01/2014 | 2014 |  | 80% | ... | 141.02 | 158.98
| Total : | 539.56 |  |  |  | 124.79 | 325.23 | 214.33
EDUCATION DEPARTMENT (S)
1 | Constn.of Auditorium of Sainik School, Imphal | 688.41 | 2016-17 | 2023-12-01 | 90% | 303.82 | 674.73 | 13.68 | ...
2 | Constn.of Girl's Hostel at (Raja Dumbra H/S Campus)Wangkhei Model High School, Imphal East Dist.,Manipur. | 661.89 | 2016-17 | 2023-12-01 | 90% | 293.72 | 650.86 | 11.03 | ...
3 | Constn. of Girls Hostel at Sainik School, Imphal | 449 | 2021-22 | 2023-12-01 | 50% | 300 | 300 | 149 | ...
4 | School Fagathansi Mission Phase II at Srivan High School, Imphal East. | 100.62 | 2022-23 | 2023-12-01 | 40% | 44.72 | 44.72 | 55.9 | ...
5 | School Fagathansi Mission Phase II at Thangmeiband Khoyathong Tombisana High School, Imphal West. | 135.01 | 2022-23 | 2023-10-01 | 90% | 60 | 60 | 75.01 | ...
6 | School Fagathansi Mission Phase II at Pettigrew Junior High School, Imphal West. | 135.02 | 2022-23 | 2024-10-01 | 90% | 60.01 | 60.01 | 75.01 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
EDUCATION DEPARTMENT (S)
7 | School Fagathansi Mission Phase II at Maklang High School, Imphal West. | 135.19 | 2022-23 | 2023-12-01 | 85% | 60.08 | 60.08 | 75.11 | ...
8 | School Fagathansi Mission Phase II at Keirenphabi Junior, High School, Bishnupur | 103.26 | 2022-23 | 2023-12-01 | 70% | 45.9 | 45.9 | 57.36 | ...
| Total : | 2,408.40 |  |  |  | 1,168.25 | 1,896.30 | 512.10
MINORITIES AND OTHER BACKWARD CLASSES (MOBC)
1 | Boys Hostel in two Higher Secondary Schools, Chandel | ₹245.55 F NO. 3/14(5)/2008-PP-I Dt. 19/10/2011 | 2011-12 | 2023 | 90% | ... | ... | 245.55 | ...
2 | Girls hostel in two Higher Secondary schools and five high schools and in three other places, Chandel | ₹818.50 F NO. 3/14(5)/2008-PP-I Dt. 19/10/2011 | 2011-12 | 2023 | 85% | ... | ... | 818.5 | ...
3 | School building in Primary Schools: (Kakodan Khullen, Muaidak, Khanpi, Phiran & Lamdan Kuki), Churachandpur | ₹137.10 F NO. 3/14(3)/2013-PP-I Dt. 26/03/2014 | 2013-14 | 2023 | 80% | 5.48 | 5.48 | 131.62 | ...
4 | School building in Primary Schools: (Phoisenbung, Songdoh, Phunchongjang, Bonglushi & Samulamlan) (5 classrooms in each school), Churachandpur | ₹137.10 F NO. 3/14(3)/2013-PP-I Dt. 26/03/2014 | 2013-14 | 2023 | 95% | 5.48 | 5.48 | 131.62 | ...
5 | Girls Hostel at SSA Residential, New Lamka, Churachandpur Govt. H/S, Hill town and at Vimala Raina H/S, HQ Veng (45 bed), Churachadpur | ₹210.00 F NO. 3/14(3)/2013-PP-I Dt. 30/09/2015 | 2015-16 | 2023 | 80% | 18.6 | 86.4 | 123.6 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MINORITIES AND OTHER BACKWARD CLASSES (MOBC)
6 | IAY, Pherzawl | ₹187.50 F NO. 13/31/2017-MsDP-MoMA Dt. 30/12/2019 | 2016-17 | 2023 | 84% | ... | ... | 187.5 | ...
7 | Sadbhavna Mandap in Chingai block, Ukhrul | ₹250.00 F NO. 13/408/2017-MsDP-MoMA Dt. 30/11/2017 | 2017-18 | 2023 | 50% | ... | 137.5 | 112.5 | ...
8 | School building of Manipur Public School (785 students,223 minorities) 14 ACRs, Imphal East | ₹122.20 F NO. MsDP-13/413/2017-MsDP-MoMA Dt. 29/12/2017 | 2017-18 | 2023 | 75% | 86.88 | 86.88 | 35.32 | ...
9 | 100 Bedded hostel at Residential School, New Lamka, Churachandpur | ₹250.00 F NO. MsDP-13/413/2017-MsDP-MoMA Dt. 28/03/2018 | 2017-18 | 2023 | 20% | 7.21 | 110.04 | 139.96 | ...
10 | Model Residential School at Singhat Block HQ, Churachandpur. | ₹2,562.00 F NO. MsDP-13/413/2017-MsDP-MoMA Dt. 28/03/2018 | 2017-18 | 2023 | 75% | 611.04 | 625.82 | 1936.18 | ...
11 | Model Residential School at Moirangpurel (Population of Students in catchment area is 800 approx. of which 80% are minorities), Imphal East. | ₹2,562.00 F NO. MsDP-13/413/2017-MsDP-MoMA Dt. 28/03/2018 | 2017-18 | 2023 | 91% | 360.88 | 360.88 | 2201.12 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MINORITIES AND OTHER BACKWARD CLASSES (MOBC)
12 | School Building, 100 bedded Girls' Hostel, compound fencing at Poiroukhongjin H/S, Imphal East. | ₹472.00 F NO. MsDP-13/413/2017-MsDP-MoMA Dt. 28/03/2018 | 2017-18 | 2023 | 90% | 91.75 | 115.16 | 356.84 | ...
13 | Upgradation of Residential School, Bendramai (8 rooms), Senapati | ₹146.00 F NO. MsDP-13/413/2017-MsDP-MoMA Dt. 28/03/2018 | 2017-18 | 2023 | 70% | 10.74 | 49.12 | 96.88 | ...
14 | Model Residential School at Senapti Dist. HQ, Senapati | ₹2,562.00 F NO. MsDP-13/413/2017-MsDP-MoMA Dt. 28/03/2018 | 2017-18 | 2023 | 85% | 923.7 | 1050.42 | 1511.58 | ...
15 | Model Residential School at Tamei Block HQ, Tamenglong | ₹2,562.00 F NO. MsDP-13/413/2017-MsDP-MoMA Dt. 28/03/2018 | 2017-18 | 2023 | 92% | 1082.2 | 1082.2 | 1479.8 | ...
16 | 100 bedded hostel at KGBV Ukhongsang Sikhong Sekmai NP, Thoubal | ₹250.00 F NO. MsDP-13/413/2017-MsDP-MoMA Dt. 28/03/2018 | 2017-18 | 2023 | 80% | 49.35 | 53.15 | 196.85 | ...
17 | Model Residential School at Heirok, Thoubal | ₹2,562.00 F NO. MsDP-13/413/2017-MsDP-MoMA Dt. 28/03/2018 | 2017-18 | 2023 | 85% | 957.98 | 1050.42 | 1511.58 | ...
18 | 100 bedded hostel at Residential School at Poi Village, Ukhrul | ₹250.00 F NO. MsDP-13/413/2017-MsDP-MoMA Dt. 28/03/2018 | 2017-18 | 2023 | 72% | 18.74 | 83.76 | 166.24 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MINORITIES AND OTHER BACKWARD CLASSES (MOBC)
19 | 100 bedded hostel at Residential School at Shangshak, Ukhrul | ₹250.00 F NO. MsDP-13/413/2017-MsDP-MoMA Dt. 28/03/2018 | 2017-18 | 2023 | 60% | 125 | 128.2 | 121.8 | ...
20 | Construction of Sadhav Mandap in Vangai Range, Pherzawl | ₹250.00 F NO. MsDP-13/124/2018-MsDP-MoMA Dt. 14/12/2018 | 2018-19 | 2023 | 90% | 50.62 | 100 | 150 | ...
21 | Constn. of 100 bedded Girls Hostel at Rahamania high School, Kshetrigao, Imphal East | ₹254.00 F NO. MsDP-13/133/2018-MsDP-MoMA Dt. 17/12/2018 | 2018-19 | 2023 | 75% | 58.2 | 68.8 | 185.2 | ...
22 | Constn. of school Building and 100 bedded Girls Hostel at Lalpani High School(Jiribam), Jiribam. | ₹382.00 F NO. MsDP-13/133/2018-MsDP-MoMA Dt. 17/12/2018 | 2018-19 | 2023 | 95% | 191 | 191 | 191 | ...
23 | Constrn. of 50 bedded Girls Hostel at Lilong Hr. Src. Madrasa Sec. School, Lilong, Thoubal | ₹254.00 F NO. MsDP-13/133/2018-MsDP-MoMA Dt. 17/12/2018 | 2018-19 | 2023 | 30% | ... | 127 | 127 | ...
24 | Construction of 50 bedded Hostel at Tamenglong College in Tamenglong Block, Tamenglong | ₹273.00 F NO. MsDP-13/134/2018-MsDP-MoMA Dt. 28/12/2018 | 2018-19 | 2023 | 20% | ... | 49.14 | 223.86 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MINORITIES AND OTHER BACKWARD CLASSES (MOBC)
25 | Sadbhavna Mandap in Thoubal DHQ, Thoubal | ₹250.00 F NO. MsDP-13/131/2018-MsDP-MoMA Dt. 03/01/2019 | 2018-19 | 2023 | 93% | 167.62 | 167.62 | 82.38 | ...
26 | Construction of ,50 bedded Girls Hostel at Chingai Govt. High School, Chingai Block, Ukhrul | ₹273.00 F NO. MsDP-13/134/2018-MsDP-MoMA Dt. 28/12/2018 | 2018-19 | 2023 | 65% | 108.5 | 122.85 | 150.15 | ...
27 | Construction of 50 bedded Girls Hostel at Manbashi Govt. High School, Kamjong Block Kamjong | ₹273.00 F NO. MsDP-13/134/2018-MsDP-MoMA Dt. 28/12/2018 | 2018-19 | 2023 | 70% | ... | 136.5 | 136.5 | ...
28 | Construction of 50 bedded Girls Hostel at Nambashi Khullen High School, Kassom Khullen, Kamjong | ₹273.00 F NO. MsDP-13/134/2018-MsDP-MoMA Dt. 28/12/2018 | 2018-19 | 2023 | 45% | ... | 136.5 | 136.5 | ...
29 | Construction of 50 bedded Girls Hostel at Mangpok Chepu High School, Ukhrul | ₹254.00 F NO. MsDP-13/134/2018-MsDP-MoMA Dt. 28/12/2018 | 2018-19 | 2023 | 75% | 34.03 | 92.97 | 161.03 | ...
30 | Sadbhav Mandop in Chandel DHQ, Chandel | ₹250.00 F NO. MsDP-13/414/2017-MsDP-MoMA Dt. 30/09/2019 | 2018-19 | 2023 | 10% | ... | 75 | 175 | ...
31 | Construction of School ,Building with Boys & Girls Toilet at Kangla Ukok Primary School, Imphal East | ₹130.99 F NO. MsDP-13/133/2018-MsDP-MoMA Dt. 30/01/2019 | 2018-19 | 2023 | 95% | 65.5 | 65.5 | 65.49 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MINORITIES AND OTHER BACKWARD CLASSES (MOBC)
32 | Construction of School ,Building with Boys & Girls Toilet at Tulihal Primary School, Imphal East | ₹130.99 F NO. MsDP-13/133/2018-MsDP-MoMA Dt. 30/01/2019 | 2018-19 | 2023 | 95% | 65.5 | 65.5 | 65.49 | ...
33 | Sadbhav Mandop in Tamenglong DHQ, Tamenglong | ₹250.00 F NO. MsDP-13/414/2017-MsDP-MoMA Dt. 30/09/2019 | 2018-19 | 2023 | 40% | 60.53 | 44.47 | 205.53 | ...
34 | Hostels (one boy & one girl), Tengnoupal | ₹508.00 F NO. MsDP-13/25/2019-MsDP-MoMA Dt. 06/01/2020 | 2018-19 | 2023 | 80% | 337.5 | 337.5 | 170.5 | ...
35 | Working Women Hostel (Kshetrigao), Imphal East | ₹1,130.00 F NO. MsDP-13/8/2020-MsDP-MoMA Dt. 23/06/2021 | 2019-20 | 2023 | 65% | 356.17 | 565 | 565 | ...
36 | Working Women Hostel Keirao), Imphal East | ₹1,130.00 F NO. MsDP-13/8/2020-MsDP-MoMA Dt. 23/06/2021 | 2019-20 | 2023 | 45% | 196.08 | 368.92 | 761.08 | ...
37 | Construction of Girls' Hostel for Minority students, Chandel | ₹250.00 F NO. MsDP-13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 85% | 125 | 125 | 125 | ...
38 | Construction of Boys' Hostel for Minority students, Chandel | ₹250.00 F NO. MsDP-13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 45% | ... | 45 | 205 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MINORITIES AND OTHER BACKWARD CLASSES (MOBC)
39 | Working Women Hostel Chandel DHQ, Chandel | ₹525.00 F NO. MsDP-13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 85% | 299.84 | 299.84 | 225.16 | ...
40 | Construction of Girls' for Hostel for Minority students, Chandel | ₹250.00 F NO. MsDP-13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 60% | ... | 45 | 205 | ...
41 | Model Residential School at Saibol Joupi, Chandel | ₹2,526.00 F NO. MsDP-13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 80% | 900.62 | 1263 | 1263 | ...
42 | Construction of Hostel for Mission Blind School, Heikakpokpi, Tengnoupal | ₹250.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 90% | 84.82 | 125 | 125 | ...
43 | Girls' hostel at Molnoi, Tengnoupal | ₹250.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 90% | 51.7 | 51.7 | 198.3 | ...
44 | Model Residential School at Moreh, Tengnoupal | ₹2,526.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 90% | 1074.23 | 1263 | 1263 | ...
45 | Working Women Hostel at Pherzawl HQ, Pherzawl | ₹525.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 70% | 194.32 | 194.32 | 330.68 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MINORITIES AND OTHER BACKWARD CLASSES (MOBC)
46 | Model Rsidential School at Boukpi, Churchandpur | ₹2,526.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 35% | 102.86 | 351.82 | 2174.18 | ...
47 | 50 bedded Girls' hostel compound fencing at Sabal Leikai HS, Khetrigao, Imphal East | ₹250.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 92% | 115.08 | 125 | 125 | ...
48 | 50 bedded Girls' hostel at Borobekra Hr. Sec. School, Jiribam | ₹250.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 95% | 112.5 | 112.5 | 137.5 | ...
49 | 50 bedded Girls' hostel at Ahammadabad Hr. Sec. with compound fencing, Jiribam | ₹250.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 95% | 112.5 | 112.5 | 137.5 | ...
50 | Model Residential School at Jiribam, Jiribam | ₹2,526.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 75% | 187.41 | 187.41 | 2338.59 | ...
51 | Working Women Hostel at Jiribam HQ, Jiribam | ₹525.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 60% | ... | 262.5 | 262.5 | ...
52 | Girls Hostel at Keithelmanbi Govt. High School, Kangpokpi | ₹250.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 50% | 83.18 | 112.5 | 137.5 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MINORITIES AND OTHER BACKWARD CLASSES (MOBC)
53 | Working Women Hostel at Senapati HQ, Senapati | ₹525.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 85% | 98.88 | 163.62 | 361.38 | ...
54 | Construction of Gallery and Sports Complex at Noney, Noney | ₹279.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 90% | 6.56 | 132.94 | 146.06 | ...
55 | Working Women Hostel at Noney HQ, Noney | ₹525.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 65% | 3.02 | 259.48 | 265.52 | ...
56 | Working Women Hostel at Tamenglong DHQ, Tamenglong | ₹525.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 40% | 169.96 | 262.5 | 262.5 | ...
57 | Construction of 50 bedded Girls Hostel at Sugunu Hr.Secondary School, Sugunu (G+I), Kakching | ₹250.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 80% | 268.58 | 168.58 | 81.42 | ...
58 | Construction of ,50 bedded Girls Hostel at Paoyi, Ukhrul | ₹250.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 85% | 56.27 | 68.73 | 181.27 | ...
59 | Model Residential School at Kamjong, Kamjong | ₹2,526.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 25% | 382.45 | 880.55 | 1645.45 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MINORITIES AND OTHER BACKWARD CLASSES (MOBC)
60 | Working Women Hostel at Kamjong HQ, Kamjong | ₹525.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 57% | ... | 26.25 | 498.75 | ...
61 | Construction of 50 bedded Girls Hostel at Kaziphung, Ukhrul | ₹250.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 50% | 25.28 | 25.28 | 224.72 | ...
62 | Working Women Hostel at Ukhrul DHQ, Ukhrul | ₹525.00 F NO. 13/23/2020-MsDP-MoMA Dt. 24/03/2020 | 2019-20 | 2023 | 95% | 236.25 | 262.5 | 262.5 | ...
63 | Staff Quarter at PHC Komlathabi, Chandel | ₹145.58 F NO. 13/36/2020-MsDP-MoMA Dt. 30/06/2020 | 2020-21 | 2023 | 35% | 72.79 | 72.79 | 72.79 | ...
64 | Staff Quarter at PHC Lai, Senapati | ₹145.58 F NO. 13/36/2020-MsDP-MoMA Dt. 30/06/2020 | 2020-21 | 2023 | 85% | 72.79 | 72.79 | 72.79 | ...
65 | Staff Quarter at PHC Chaton, Tamenglong | ₹145.58 F NO. 13/36/2020-MsDP-MoMA Dt. 30/06/2020 | 2020-21 | 2023 | 60% | 33.97 | 38.82 | 106.76 | ...
66 | Staff Quarter at PHC Khoupum, Noney | ₹145.58 F NO. 13/36/2020-MsDP-MoMA Dt. 30/06/2020 | 2020-21 | 2023 | 95% | 119.36 | 119.36 | 26.22 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MINORITIES AND OTHER BACKWARD CLASSES (MOBC)
67 | Staff Quarter at PHC Angtha, Imphal East | ₹145.58 F NO. 13/36/2020-MsDP-MoMA Dt. 30/06/2020 | 2020-21 | 2023 | 70% | 36.44 | 36.44 | 109.14 | ...
68 | Construction of PHC building at Oinam Hill, Senapati | ₹145.58 F NO. 13/36/2020-MsDP-MoMA Dt. 30/06/2020 | 2020-21 | 2023 | 95% | 71.21 | 71.21 | 74.37 | ...
69 | Construction of Science & Commerce Block at Tamenglong College with laboratory faciliaties, compound fencing, Tamenglong | ₹1,500.00 F NO. 13/5/2021-MsDP-MoMA Dt. 26/03/2021 | 2020-21 | 2024 | 22% | 268.97 | 481.03 | 1018.97 | ...
70 | Infrastructure Development of Pettigrew College at Ukhrul District, Ukhrul | ₹3,864.70 F NO. 13/19/2021-MsDP-MoMA Dt. 07/06/2021 | 2020-21 | 2023 | 45% | 1705.17 | 1932.36 | 1932.34 | ...
71 | Construction of 50 bedded Boys Hostel at Moreh College, Tengnoupal | ₹489.59 F NO. 13/19/2021-MsDP-MoMA Dt. 07/06/2021 | 2020-21 | 2023 | 60% | 222.75 | 244.8 | 244.79 | ...
72 | 50 bedded Hostel at Jessami Hr. Sec. School. UDISE CODE: 14080202501., Ukhrul | ₹247.70 F NO. 13/19/2021-MsDP-MoMA Dt. 07/06/2021 | 2020-21 | 2023 | 76% | 123.85 | 123.85 | 123.85 | ...
73 | 50 bedded Girls Hostel at Sardar Patel H/S, Mao Gate. UDISE CODE : 10410510001., Senapati | ₹247.70 F NO. 13/19/2021-MsDP-MoMA Dt. 07/06/2021 | 2020-21 | 2023 | 59% | 172.92 | 172.92 | 74.78 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MINORITIES AND OTHER BACKWARD CLASSES (MOBC)
74 | 50 bedded Girls Hostel at Purul HR.Sec. School UDISE CODE : 14010600401., Senapati | ₹247.70 F NO. 13/19/2021-MsDP-MoMA Dt. 07/06/2021 | 2020-21 | 2023 | 60% | 105.05 | 123.85 | 123.85 | ...
75 | 50 bedded Girls Hostel at Purul Paocham HR.Sec. School UDISE CODE : 14080204101., Ukhrul | ₹247.70 F NO. 13/19/2021-MsDP-MoMA Dt. 07/06/2021 | 2020-21 | 2023 | 30% | ... | 123.85 | 123.85 | ...
76 | 50 bedded Girls Hostel at Moreh College, Tengnoupal | ₹489.59 F NO. 13/19/2021-MsDP-MoMA Dt. 07/06/2021 | 2020-21 | 2023 | 82% | 339.41 | 339.41 | 150.18 | ...
77 | 50 bedded Girls Hostel at Liyai Khullen Hr.Sec. School UDISE CODE : 14010405301, Senapati | ₹247.70 F NO. 13/19/2021-MsDP-MoMA Dt. 07/06/2021 | 2020-21 | 2023 | 65% | 158.74 | 158.74 | 88.96 | ...
78 | 50 bedded Girls Hostel at Larong Govt. H/S UDISE CODE : 14090310801, CHANDEL | ₹247.70 F NO. 13/19/2021-MsDP-MoMA Dt. 07/06/2021 | 2020-21 | 2023 | 80% | 180.05 | 180.05 | 67.65 | ...
79 | 50 bedded Girls Hostel at Kangbarol UPS UDISE CODE : 14090420101. Student enrolment +125, Chandel | ₹247.70 F NO. 13/19/2021-MsDP-MoMA Dt. 07/06/2021 | 2020-21 | 2023 | 60% | 60.45 | 63.4 | 184.3 | ...
80 | 50 bedded Girls Hostel at KGBV, Mandeu. UDISE CODE : 14020202302, Tamenglong | ₹247.70 F NO. 13/19/2021-MsDP-MoMA Dt. 07/06/2021 | 2020-21 | 2023 | 35% | 60.84 | 63.01 | 184.69 | ...
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MINORITIES AND OTHER BACKWARD CLASSES (MOBC)
81 | 50 bedded Boys' Hostel at Liwachangning H/S UDISE CODE : 14090312501, Chandel | ₹247.70 F NO. 13/19/2021-MsDP-MoMA Dt. 07/06/2021 | 2020-21 | 2023 | 90% | 199.52 | 199.52 | 48.18 | ...
82 | 51 bedded Boys' Hostel at Khangbarol UPS. UDISE CODE : 14090420101, Chandel | ₹247.70 F NO. 13/19/2021-MsDP-MoMA Dt. 07/06/2021 | 2020-21 | 2023 | 68% | 135.8 | 135.8 | 111.9 | ...
83 | Construction of Joint Tribes Council Office Building in Tamenlong | ₹300.00 F NO. SCHEM-4/32/2021-MsDP-MoMA Dt. 20/09/2021 | 2021-22 | 2023 | 40% | 115.11 | 184.89 | 115.11 | ...
84 | Construction of Haj House at Lilong, Thoubal | ₹1,000.00 F NO. PLG2-7/4/2022-PLG-PLANNING- Part (12) Dt. 13/12/2022 | 2022-23 | 2023 | 30% | 400 | 400 | 600 | ...
85 | Construction of Indigenous Sport Complex in Senapati | ₹1,507.00 F NO. PLG2-7/4/2022-PLG-PLANNING- Part (21) Dt. 20/04/2023 | 2022-23 | 2023 | 10% | 200 | 200 | 1307 | ...
86 | 550 Nos. of walls under PMKSY-HKKP-GW | ₹ 6,168.00 8/29/2019 -MID (HKKP-GW)dt. 23/09/2016 | Sept., 2020 | May, 2022 | 80% | 296.88 | 4243.88 | 1924.12 | ...
| Total | 61580.29 |  |  |  | 15889.66 | 24454.47 | 37125.82
MANIPUR STATE POWER COMPANY LIMITED
1 | Installation of 400 KV SS at Thoubal (NLCPR) | 24362 | 2015 | 2018 |  | ... | 22972.99 | 1389.01
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MANIPUR STATE POWER COMPANY LIMITED - Contd.
2 | Construction of 400 KV Line on D/C Towers initially charged at 132 KV from Yurembam to Thoubal via Nambol in Manipur (NLCPR) | 27267.85 | 2016 | 2018 |  | ... | 24099.43 | 3168.42
3 | Installation of 2 Nos. of line bays at Imphal (PG) SS (State Plan) | 3524.08 | 2016 | 2018 |  | ... | 3411.56 | 112.52
4 | Installation of 132/33 KV SS at Hundung (Ukhrul) & its associated line (SPA) | 5130 | 2008 | 2017 |  | ... | 5122.82 | 7.18
5 | Renovation & Modernisation of 132/33 KV SS at Yurembam (SPA/NEC) | 4736.73 | 2008 | 2018 |  | ... | 4682.68 | 54.05
6 | Renovation & Modernisation of three No.s of 132/33 KV SS at Kakching , Karong & Churchandpur. | 5498.59 | 2014 | 2016 |  | ... | 4919.69 | 578.9
7 | Installation of 2x20 MVA, 132 KV Substation along with associated 132 KV LILO line & related works at Thoubal | 5205.77 | 2015 | 2017 |  | ... | 4368.53 | 837.24
8 | Stringing of 132 KV line (2nd circuit) from Kakching to Churchandpur | 1792.06 | 2015 | 2017 |  | ... | 1635.32 | 156.74
9 | Installation of 2x12.5 MVA, 132/33 KV Sub-station at Thanlon with associated 132 KV line and related civil works on turn-key basis under NLCPR | 14238 | 2014 | 2018 |  | ... | 13497.01 | 740.99
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MANIPUR STATE POWER COMPANY LIMITED - Contd.
10 | Installation of 132/33 KV SS at Moreh with erection of associated 132 KV line (NLCPR) | 11924 | 2015 | 2018 |  | ... | 10193.12 | 1730.88
11 | Augmentation of Rengpang 132/33 KV Sub-station by installing (3x4.16+1x4.16)MVA 132/33 KV single phase transformers | 1263.42 | 2015 | 2016 |  | ... | 1237.31 | 26.11
12 | Construction of 132/33 KV S/C line (2nd Ckt) on D/C towers from Leimatak PH (NHPC) to 132 KV SS at Ningthoukhong | 1943.83 | 2015 | 2019 |  | ... | 1941.31 | 2.52
13 | Installation of 132 KV Sub-station along with associated 132 KV Line at Elangkhangpokpi | 5621 | 2015 | 2018 |  | ... | 4790.77 | 830.23
14 | Construction of 132 KV S/C line (3nd Ckt) strung on D/C towers from 132 KV Yurembam SS (state) to Yurembam SS (PGCIL) | 1024.64 | 2015 | 2018 |  | ... | 856.47 | 168.17
15 | Installation of 1x20 MVA transformer at Yaingangpokpi | 613.29 | 2015 | 2017 |  | ... | 600.92 | 12.37
16 | Construction of 132/33 KV SS at Tipaimukh | 5139 | 2015 | 2018 |  | ... | 4760.86 | 378.14
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MANIPUR STATE POWER COMPANY LIMITED - Contd.
17 | Construction of 132 KV link Transmission line from 400/132 KV SS Thoubal at Kongba, Yaingangpokpi and Hundung on existing Kongba to Kakching 132 KV T/L | 1583 | 2016 | 2020 |  | 111.01 | 1478.76 | 104.24
18 | Construction of 132 KV link Transmission line from 400/132 KV SS Thoubal to 132 KV SS at Kakching & Chandel on existing Kongba to Kakching132 KV T/L | 797.72 | 2016 | 2020 |  | ... | 600 | 197.72
19 | Construction of 132 KV link Transmission line from 400/132 KV SS Thoubal to 132 KV SS at Moreh on 132 KV T/L (ongoing) | 2233.52 | 2016 | 2020 |  | 159.42 | 1520.93 | 712.59
20 | Providing of Energy Meter | 381 | 2015 | 2016 |  | ... | 378.16 | 2.84
21 | Augmentation of 132/33 KV Sub-station at Jiribam (Installation of additional transformers). | 515.87 | 2015 | 2016 |  | ... | 481.29 | 34.58
22 | Renovation & Modernisation of 2 Nos. of 132/33 KV SS at Yangangpokpi & Ningthoukhong - 1st Phase on turn - key basis | 4050 | 2012 | 2015 |  | ... | 3676.15 | 373.85
23 | Renovation & Upgradation of grid Sub-Station of MSPDCL under PSDF | 5005.65 | 2017 | 2019 |  | ... | 4643.11 | 362.54
24 | Installation of 2x 12.5 MVA, 132 KV Sub- Station along with the associated 132 KV line and related works at Chandel | 3291.74 | 2009 | 2015 |  | ... | 3184.54 | 107.2
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MANIPUR STATE POWER COMPANY LIMITED - Contd.
25 | Installation of 132 KV line bay equipment at Ningthoukhong & Churachandpur 132/33 KV SS for 2nd 132 KV Transmission line from Ningthoukhong & Churchandpur | 429.24 | 2008 | 2010 |  | ... | 362.17 | 67.07
26 | Construction of 132 KV SC Transmission line from Yurembam to Yaingangpokpi 132 Kv Sub-Station | 3522.65 | 2008 | 2015 |  | ... | 3498.09 | 24.56
27 | Installation of 33/11 Kv sub station at Mayangkhang with associated 33 KV | 963.12 | 2015 | 2017 |  | ... | 936.84 | 26.28
28 | Installation of 33/11 Kv sub station at Mao with associated 33 KV line | 1021 | 2015 | 2017 |  | ... | 1008 | 13
29 | Installation of 33/11 KV SS(2x1 MVA)SS at Gamphazol with associated 33 KV line | 1006 | 2015 | 2017 |  | ... | 957.77 | 48.23
30 | Erection of 33 KV feeders from Yurembam Power Grid SS (SCA) | 2143.37 | 2013 | 2017 |  | ... | 2141.64 | 1.73
31 | Installation of 33/11 KV SS (2x1 KVA )SS at Nungbi Khullen with associated 33 KV line (NLCPR) | 1594.81 | 2014 | 2017 |  | ... | 1540.13 | 54.68
32 | Installation of 2x5 MVA 33/11 KV SS with associated 33 KV line at Power House site of Loktak Downstream HE Project (NEC) | 1484 | 2014 | 2017 |  | ... | 1442.08 | 41.92
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MANIPUR STATE POWER COMPANY LIMITED - Contd.
33 | Renovation of 33/11 KV SS at Khoupum | 505.82 | 2016 | 2018 |  | ... | 421.29 | 84.53
34 | Renovation of 33/11 KV SS (2x1 MVA)SS at Paoyi at Ukhrul | 915.49 | 2016 | 2018 |  | ... | 494.91 | 420.58
35 | Installation of 33/11 KV SS at Thuyeng at Senapati | 1402.79 | 2016 | 2018 |  | ... | 746.38 | 656.41
36 | Construction of 33 KV D/C line STP from 132/33 KV sub- station at Thoubal to 33/11 KV S/S at Thoubal (old) | 1183.04 | 2016 | 2020 |  | ... | 1172.85 | 10.19
37 | Installation of 2x2.5 MVA, 33/11 KV SS along with associated 33 KV line & related Civil Works at GUMNOM, Ukhrul District, on turnkey basis. | 952.64 | 2015 | 2016 |  | ... | 859.04 | 93.6
38 | Installation of 1x3.15 MVA KV SS along with associated 33 KV line & related Civil Works at Heirok (Heirok Thokchom Leikai) | 1029.44 | 2016 | 2018 |  | ... | 741.97 | 287.47
39 | Installation of 1x3.15 MVA KV SS along with associated 33 KV line & related Civil Works at Yairipok | 1077.38 | 2016 | 2018 |  | ... | 741.57 | 335.81
40 | Installation of 1x3.15 MVA KV SS along with associated 33 KV line & related Civil Works at Wangoi | 966.93 | 2016 | 2018 |  | ... | 594.16 | 372.77
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MANIPUR STATE POWER COMPANY LIMITED - Contd.
41 | Installation of 1x3.15 MVA KV SS along with associated 33 KV line & related Civil Works at Wangjing (Khangabok Moirang Palli Bazar) | 1077.38 | 2016 | 2018 |  | ... | 805.05 | 272.33
42 | Augmentation of 33/11 KV Sub-station (from 1x3.5MVA to 2x5MVA, 33/11 Kv SS, at Kangpokpi | 142.4 | 2016 | 2017 |  | ... | 46.85 | 95.55
43 | Augmentation of 33/11 KV Sub-station (from 1x3.5MVA to 2x5MVA, 132/33 Kv SS, at Karong | 197.57 | 2016 | 2017 |  | ... | 122.87 | 74.7
44 | Re-stringing & Strengthening of 33 KV line. (Phase-I) I) Hundung to Tolloi. II) Hundung to Kamjong (III) Napetpalli to Saikul | 306.58 | 2015 | 2017 |  | ... | 263.95 | 42.63
45 | Re-stringing & Strengthening of 33 KV line. (Phase-I) I) Bishnupur to Churachandpur via Ningthoukhong and Moirang (II) Churachandpur to Singhat | 215.6 | 2018 | 2020 |  | ... | 212.2 | 3.4
46 | Re-string 33 KV line Utlou to Mayang Imphal | 111.07 | 2020 | 2023 |  | ... | 96.13 | 14.94
47 | Re-string 33 KV line Khuman Lampak to Kongba | 110.19 | 2020 | 2023 |  | ... | 94.42 | 15.77
48 | Re-string 33 KV Jiribam to Oinamlong | 107.63 | 2019 | 2021 |  | ... | 75.34 | 32.29
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MANIPUR STATE POWER COMPANY LIMITED - Contd.
49 | Re-string 33 KV Yurembam to Leimakhong | 107 | 2019 | 2021 |  | ... | 75.34 | 31.66
50 | PSDF-5 (Installation of Reactive power Solution on 33/11 KV SS in Manipur | 2554.88 | 2020 | 2022 |  | 22.81 | 2178.41 | 376.47
51 | Installation of 2x2.5 MVA 33/11 KV substation along with associated 33 KV line and related Civil works at Phungyar Ukhrul Dist. on TKB | 1086.09 | 2015 | 2017 |  | ... | 1054.33 | 31.76
52 | Installation of 2x2.5 MVA 33/11 KV substation along with associated 33 KV line and related works at Gelnel, Senapati Dist. on TKB | 780.51 | 2014 | 2017 |  | ... | 718.17 | 62.34
53 | Installation of 2x2.5 MVA 33/11 KV substation along with associated 33 LILO line and related Civil works at Khasom Khullen Ukhrul Dist. on TKB | 1042.26 | 2015 | 2018 |  | ... | 1037.36 | 4.9
54 | Construction of DC transmission line from Leimakhong to Iroisemba on turnkey basis (Supply and Erection) | 1309.64 | 2008 | 2015 |  | ... | 1192.64 | 117
55 | Annual Maintenance Contect Service for SCADA system at Yurembam | 177.62 |  |  |  | ... | 156.31 | 21.31
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MANIPUR STATE POWER COMPANY LIMITED - Contd.
56 | Assessment and firming up of hydro power potential in Manipur including preparation of identification report and physical marking of power domain site | 185.61 |  |  |  | ... | 185.61 | ...
57 | Main SCADA EMS system of SLDCs under project "Expansion of SCADA EMS system of SLDCs of North Eastern region | 793.09 |  |  |  | 119.42 | 790.54 | 2.55
58 | Installation of 2x5 MVA, 33/11 KV sub-station along with the associated 33 KV line & related Civil works at Joujanktek, Noney Dist. on turnkey basis. | 1400.19 | 2019 | 2023 |  | ... | ... | 1400.19
59 | Installation of 2x5 MVA, 33/11 KV sub-station along with the associated 33 KV line at Oinam, Senapati Dist. on turnkey basis. | 1330.76 | 2019 | 2023 |  | ... | ... | 1330.76
60 | Installation of 2x5 MVA, 33/11 KV sub-station along with the associated 33 KV line at Nampisha, Kamjong Dist. on turnkey basis. | 1193.27 | 2019 | 2023 |  | ... | ... | 1193.27
61 | Installation of 2x5 MVA, 33/11 KV sub-station along with the associated 33 KV line at Chingai, Ukhrul Dist. on turnkey basis. | 1262.46 | 2019 | 2023 |  | ... | 558.88 | 703.58
Appendix - IX - Contd.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MANIPUR STATE POWER COMPANY LIMITED - Contd.
62 | Installation of 2x5 MVA, 33/11 KV sub-station along with the associated 33 KV line at Somdal, Ukhrul Dist. on turnkey basis. | 1055.87 | 2019 | 2023 |  | ... | 467.11 | 588.76
63 | Installation of 2x5 MVA, 33/11 KV sub-station along with the associated 33 KV line at Liyaikhunou, Senapati Dist. on turnkey basis. | 1127.2 | 2019 | 2023 |  | ... | 257.99 | 869.21
64 | Installation of 2x5 MVA, 33/11 KV sub-station along with the associated 33 KV line at Kachai, Ukhrul Dist. on turnkey basis. | 1124.28 | 2019 | 2023 |  | ... | ... | 1124.28
65 | Installation of 2x5 MVA, 33/11 KV sub-station along with the associated 33 KV line at Sanakeithel, Ukhrul Dist. on turnkey basis. | 1138.51 | 2019 | 2023 |  | ... | 503.19 | 635.32
66 | Installation of 2x5 MVA, 33/11 KV sub-station along with the associated 33 KV line at Nambashi, Kamjong Dist. on turnkey basis. | 1193.27 | 2019 | 2023 |  | ... | ... | 1193.27
67 | Installation of 2x5 MVA, 33/11 KV sub-station along with the associated 33 KV line at Khongjaron, Tamenglong Dist. on turnkey basis. | 769.13 | 2019 | 2023 |  | ... | ... | 769.13
Appendix - IX - Concld.
COMMITMENT OF THE GOVERNMENT-LIST OF INCOMPLETE CAPITAL WORKS AS ON 31 MARCH 2023
(₹1.00 crore and above as on 31 March 2023)
(` in lakh)
Sl. No. | Name of the Project/Works | Estimated cost of works | Year of commencement | Target year of completion | Physical Progress of Work (in %) | Expenditure during the year | Progressive Expenditure to the end of the year | Pending Payments | Revised cost, if any, date of Sanction | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
MANIPUR STATE POWER COMPANY LIMITED - Concld.
68 | Installation of 2x5 MVA, 33/11 KV sub-station along with the associated 33 KV line at Ibudhou Marjing Imphal East Dist. on turnkey basis. | 1016.26 | 2019 | 2023 |  | ... | 107.83 | 908.43
69 | Installation of 2x5 MVA, 33/11 KV sub-station along with the associated 33 KV line at Akampat, Imphal East Dist. on turnkey basis. | 959.05 | 2019 | 2023 |  | 37.59 | 731.55 | 227.5
70 | Installation of 2x5 MVA, 33/11 KV sub-station along with the associated 33 KV line at Gwakhal, Jiribam Dist. on turnkey basis. | 876.41 | 2019 | 2023 |  | ... | ... | 876.41
71 | 33 KV system Integration with SLDC system in Manipur on turnkey basis. | 2480.67 | 2022 | 2024 |  | 1096.13 | 1480.13 | 1000.54
72 | Cosultancy for Hydro Investigation | 1185.69 | 2021 | 2023 |  | ... | ... | 1185.69
| Total: | 185758.62 |  |  |  | 1546.38 | 155924.82 | 29833.8